## Sheet1
Task No | Task | Duration [Hours] | Predecessor | 0.25 | 0.5 | 0.75 | 1 | 1.25 | 1.5 | 1.75 | 2 | 2.25 | 2.5 | 2.75 | 3 | 3.25 | 3.5 | 3.75 | 4 | 5
1 | Create task list | 0.5
2 | Create Gantt chart | 0.5 | 1
3 | Create a diagram of major tasks | 0.5 | 2
4 | Identify critical path | 0.5 | 3
5 | Calculate total time expected for the project | 0.5 | 4
6 | Calculate float/slack time for tasks not on critical path | 0.5 | 4
7 | Configure controls to start game with arrow keys | 0.5 | 5 | [16 empty] | 45 minutes
8 | Update snake graphic | 1 | 5 | [16 empty] | 1 minute
9 | Update food pellet graphic | 1 | 5 | [16 empty] | 1 minute
10 | Change starting position of snake for each game | 1 | 5 | [16 empty] | .5 hours
11 | Remove pop-up message box and include in the form | 0.5 | 5
12 | Make the form not resizeable | 0.083 | 5 | [16 empty] | 2 minutes
13 | Add high score list | 0.5 | 5 | [16 empty] | 20 minutes
14 | Create second Gantt chart (actual completion) | 0.5 | 7-13
| Total Time | 8.083