## Sheet1
Task No | Task | Duration [Minutes] | Predecessor | 5 | 10 | 15 | 20 | 25 | 30 | 35 | 40 | 45 | 50 | 60 | 65 | 70 | 75 | 80 | 85 | 90 | 95 | 100 | 105 | 110 | 115 | 120 | 125 | 130 | 135
1 | Create task list | 20 | bar: 5 to 20
2 | Create Gantt chart | 15 | 1 | bar: 25 to 35
3 | Create a diagram of major tasks | 30 | 2 | bar: 40 to 70
4 | Identify critical path | 5 | 3 | bar: 75
5 | Calculate total time expected for the project | 5 | 4 | bar: 80
6 | Calculate float/slack time for tasks not on critical path | 5 | 4 | bar: 80
7 | Configure controls to start game with arrow keys | 45 | 5 | bar: 85 to 125
8 | Update snake graphic | 1 | 5
9 | Update food pellet graphic | 1 | 5
10 | Change starting position of snake for each game | 30 | 5 | bar: 80 to 105
11 | Make the form not resizeable | 2 | 5
12 | Add high score list | 20 | 5 | bar: 80 to 95
13 | Create second Gantt chart (actual completion) | 10 | 13 | bar: 130 to 135
| Total Project Time (Hours): | 3.15